## Sheet1
TREE PROTECTION PLAN - New sidewalk |  |  |  | Note: refer to Tree Protection Requirements For The Department
Project: Forest Knolls Elementary School new sidewalk |  |  |  | Of Transportation for Standard Tree Protection Measures
Project Manager: William Wu |  |  |  | Note: Inspection of worksite tree protection measures required
5.25.2023 |  |  |  | by Certified Arborist with the county prior to construction activities
DBH = diamater (in.) at breast height (4.5 ft above ground), ms = multi stem |  |  |  | Note: ROW not to be utilized for staging area unless otherwise permitted
Location: F = front, S = side, R = rear, I = island, P = private, O = opposite, M = median |  |  |  | by Certified Arborist
Recommendation: F = Fencing required, s/w = sidewalk, elev = elevation pruning
DW = dead wood removal, d/w = driveway, cli = clear light, csi = clear sign, cpt = clear private tree, clh = clear house, ROW = right of way, elev = elevattion pruning
ADDRESS | SPECIES | Location | DBH | RECOMMENDATIONS
Note: All trees listed below require tree protection fencing unless noted otherwise
Ladson Rd |  |  |  | Row 11' from curb
318 | Silver Maple | 1F-P | 36 | Air excavation required, 5' s/w at curb. Note: tree in poor condition, thin canopy, 80% canopy loss.
316 | Ash | 1F-P | 34 | Air excavation required, 4-5' s/w at curb
314 | Crape Myrtle | 2F-P | 18 ms | 5' s/w at curb for possible tree planting behind s/w
| Red Maple | 1F-P | 27.5 | Air excavation required, 5' s/w at curb for possible tree planting behind s/w
310 | Silver Maple | 1F | 51 | REMOVE: poor condition, thin canopy with approx 70% canopy loss, decay in codom stem
5' s/w with 5' green space. Note: tree marked for removal 5.23.23
312 | no ROW trees
308 | no ROW trees
306 | no ROW trees
304 | no ROW trees
302 | Red Maple | 1F | 32 | Insufficient space at tree for 4'+ s/w construction. Extensive surface roots. Shift curb line and install sidewalk within existing roadway footprint, or must be removed.
Tree located 1' from curb. 5' s/w with 5' + green space for possible tree planting
10602 Ordway Dr | Red Maple | 1S | 27 | REMOVE: poor condition, decay on codom stems, poor structure. Note: Tree marked for removal 5.23.23
Marvin Rd |  |  |  | Row 11' from curb
10600 Ordway Dr | no ROW trees
303 | no ROW trees
305 | no ROW trees
307 | Norway Spruce | 1F | 17.5 | REMOVE: Evergreen trees not approved for Right of way planting. Insufficient space at tree for
sidewalk construction. 5' s/w with 5' green space for possible tree planting
Tree located 7'-6" from curb.
309 | Cherry | 1F-P | 51 | Air excavation required, elev tree 8' over s/w, 4' s/w behind pole
| Cherry | 2F-P | 31 | Air excavation required, elev tree 8' over s/w, 5' s/w with 3' green space
311 | no ROW trees
313 | no ROW trees
315 | Dogwood | 1F-P | 9 | 5' s/w with green space, root prune up to edge of s/w, elev tree 8' over s/w
Notes:
1. Mechanical root pruning is not allowed. Hand prune roots where "root prune up to edge of proposed sidewalk" is noted above.
*All root pruning shall be done to a maximum depth of 6"
2. Any roots 2" diameter or larger exposed by air excavation, that require removal due to construction activities, must be inspected by ISA certified arborist within the Tree Maintenance
Section prior to removal. Inspection will determine if tree requires removal due to required root removal.
3. An approved contractor (Licensed Tree Expert) certified in the State of Maryland for air excavation will be required to conduct all excavation where "Air Excavation Required" is noted
above.
4. Arborist (Tree Maintenance Section, Division of Highway Services) shall be notified by Project Manager of root pruning and Air Excavation schedule prior to scheduled work.
5. Excavation for proposed sidewalk shall be no more than 6"
6. Flexible, porous paving option should be considered in instances where surface roots would allow no more than 2" bridging over top of root(s).